## Slide 1
GSA Agile BPA
Prototype Implementation
6/21/2015 – 6/26/2015 Timelines
JUNE 2015
NETE = NET EFFECT
INTEGRATED MANAGEMENT COSULTING l ENTERPRISE ARCHITECTURE l TECHNOLOGY SOLUTIONS l WEB l INTERACTIVE

## Slide 2
2
Project PeachTree Scope
PeachTree application is targeted towards Medical Practitioners including Doctors, Nurses, Researchers and general public who is interested in finding out the adverse effects of Drugs, Devices and Vaccines.
This app attempts to answer a simple user story: "What drugs have adverse events, how serious are they and who reports them and other related requests e.g. User Dashboard, Reporting, Visualization etc.
The tool is built using Agile methodology Scrum Framework and is planned around Product Backlog.
For planning purposes, the project is divided into five sprints, each sprint being one day in length and each sprint will result in a deployed release.
Supported Browsers are IE10 and Chrome
The CodeBase and technical design documents are being stored in GitHub under the repository “PeachTree”.

## Slide 3
3
Project PeachTree Scope
Product Backlog
Build a system/tool to report side effects of adverse Drugs, Vaccines and Devices
Identify the Data Set
User Profile Management – User authentication and Authorization – Medium Priority, High Complexity
Provide Summary visualizations in form of charts for all 3 entities – High Priority, Medium Complexity
Get TOP 1000 drug names by AE count – High Priority, Medium Complexity
Provide Item details including the effects and when it was reported – Medium priority, Medium Complexity
Ability to report a side effect – Medium priority, High Complexity
Search Products (Drugs, Vaccines and Devices) with Adverse Effects – LOW Priority, High Priority
Ability to add alerts for a specific entity for updated AE – Low priority
Provide Filter capability – Low Priority, High Priority
Get count of patient reactions related to a drug – Low priority
Return the list of All Drugs – Low Priority
Request Top 1000 pharmacy classed by count of AEs – Low priority

## Slide 4
4
Project PeachTree Sprint Plan
6/21/2015 – KickOff Meeting
Identify Scope and Data Sets
Setup GitHub repository
Get the Team together
6/22/2015 – Sprint 1
Identify Data Set
Setup the Project framework
Develop the use case - Create a page for returning the list of TOP 1000 drugs
Automated test framework added to repository
6/23/2015 – Sprint 2
Develop the use case – Item Details Page
Create working design prototype for the ToBeReleased Product
Set up continuous Integration
Create wireframes for Sprint 3 and Sprint 4 Items
Start working on DB Model
Setup the Cloud infrastructure
Interview User Community and incorporate feedback into the Backlog

## Slide 5
5
Project PeachTree Sprint plan - Contd
6/24/2015 – Sprint 3
Deploy the application into cloud
Setup Continuous monitoring
Develop the use case - Visualize summary charts (adverse effects) for all drugs over time
Perform Usability Tests
6/25/2015 – Sprint 4
Perform regression test
Sprint Retrospective Meeting
GoLive

## Slide 6
6
THANK YOU